## Sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Define Research Objectives and planning | bar: Week 1 to Week 2
Define specific research objectives | bar: Week 1 to Week 2
Review relevant literature | bar: Week 1
Articulate the significance of the study | bar: Week 2
Develop Hypotheses and Framework | bar: Week 3 to Week 4
Develop a conceptual framework | bar: Week 3
Identify variables and define key terms | bar: Week 3 to Week 4
Design Research Methodology | bar: Week 5 to Week 6
Select the appropriate research design (comparative study) | bar: Week 5
Develop data collection methods. | bar: Week 6
Data Collection | bar: Week 7 to Week 8
Begin collecting dataset of UK Road Traffic accident | bar: Week 7 to Week 8
Preparing ethical approvals and permissions | bar: Week 8
Data Analysis Plan | bar: Week 8 to Week 10
Evaluate Statistical methods for analysis | bar: Week 8 to Week 9
Develop a data analysis plan | bar: Week 9 to Week 10
Implementation Stage | bar: Week 11 to Week 12
compare findings, patterns and correlations. | bar: Week 11 to Week 12
Reporting | bar: Week 7 to Week 14
Begin drafting the research report. | bar: Week 7 to Week 13
Organize the report with clear sections | bar: Week 14
Proof Reading and Finalise